SAMSUNG

Big Data Course

Capstone Project

Action Plan

HandAI Vietnamese Handwriting Recognition System

Nguyen Van Duy Manh  ·  Tran Hoai Nam

Baseline delivery period  01–30 September 2026

For students  Instructor review required

©2023 SAMSUNG. All rights reserved.

Samsung Electronics Corporate Citizenship Office holds the copyright of this document.

This document is protected by copyright law. Reprint and reproduction require permission.

Use outside the Samsung Innovation Campus curriculum requires written consent from the copyright holder.

1  Project Overview

Thirty-day delivery plan with traceable source images and actual app results

HandAI converts photographed Vietnamese handwriting into line-level text while preserving the reviewer’s control over segmentation and the final transcription. The plan prioritizes traceable evidence, human verification and a reproducible handoff over unsupported headline accuracy claims.

| Course | Big Data Course |
| --- | --- |
| Team | HandAI · Nguyen Van Duy Manh · Tran Hoai Nam |
| Project title | HandAI - Vietnamese Primary School Handwriting Recognition System |
| Goal | Deliver a mobile-to-AI handwriting workflow that preserves raw OCR, optional language advice and the human-selected result. |
| Primary users | Students, teachers and reviewers who need inspectable line segmentation and editable transcription. |
| Decision authority | The human reviewer confirms or edits each line. The system does not perform automated grading. |

1.1  Planned workflow

| CAPTURE | → | REVIEW LINES | → | CRNN + CTC | → | AI ADVICE | → | VERIFY |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

1.2  Prototype evidence

| Actual stored source image · original proportions | Actual app line review · 12 returned boxes |
| --- | --- |
| Source: actual persisted page image | Actual app trial 400b509c-bded-44c0-add3-f3f74ee102c4 |

2  Method and Evidence Baseline

Model handoff evidence, provisional local candidates and the actual app demonstration retain separate scopes

2.1  Implementation method

| Step | Stage | Action | Evidence |
| --- | --- | --- | --- |
| 1 | Acquire and crop | Camera or gallery input; preserve orientation and crop coordinates. | Page image and crop metadata |
| 2 | Detect lines | Preprocess ruled notebook images and return editable line boxes. | Reviewed line regions |
| 3 | Recognize | Run the packaged CRNN with CTC decoding on each confirmed crop. | Raw text, measured CRNN score and CRNN_CTC_SOFTMAX provenance |
| 4 | Advise | Request actual image-backed provider suggestions; retain model/status provenance and honest unavailable states. | Optional candidates |
| 5 | Verify | Keep raw text, select a suggestion, edit manually or skip the line. | Final text and decision source |
| 6 | Measure | Score OCR and actual AI output on the same explicit references; retain unavailable states. | Exact matches; corpus CER/WER; image/line denominators |

2.2  Verified baseline and claim boundaries

| Evidence | Recorded value | Source | Use rule |
| --- | --- | --- | --- |
| Training split | 59,462 samples | Model manifest | Recorded handoff evidence |
| Validation split | 500 samples | Model manifest | Recorded split; not a new test run |
| Model result | CER 11.3388% at step 16,900 | Checkpoint manifest | Primary recorded model metric |
| Local collection | 510 line candidates | Local manifests | All provisional and pending review |
| Actual app audit | 1 image / 1 GUI trial / 12 references. OCR 6/12 (50.00%); Groq 7/12 (58.33%). Raw CER 4.12%, WER 18.75%; AI CER 2.58%, WER 10.42%. | Persisted GUI trial · 2 Oct 2026 | One development image. References entered in app analytics after inference; not an independent test. Groq improved 4 lines, damaged 3; Gemini unavailable. |

2.3  Acceptance criteria

One traceable notebook sample can be followed from image and detected lines to raw CRNN output, reviewer action and final stored decision.

Raw OCR, advisor suggestions and final human text remain separate fields with visible provenance.

Recognition Summary separates original OCR and AI-only stages, exposes image/line/reference counts and keeps history on a separate page with selected/all deletion and incomplete-record cleanup.

General recognition accuracy and automated grading or retraining are not claimed. Any OCR-versus-AI change is limited to the disclosed image and reference lines.

3  Thirty-Day Delivery Plan

Thirty-day capstone schedule aligned with the editable WBS · 01–30 September 2026

| Phase | Days | Dates | Workstream | Owner | Primary output | Quality gate |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | D1-D5 | 01-05 Sep | Planning and evidence audit | Both | Approved scope, stakeholder needs, research questions, architecture and evidence map | Scope and claims reviewed |
| 2 | D6-D12 | 06-12 Sep | Data and image pipeline | Both | Reviewed manifests, preprocessing, crop mapping, line detector and overlay QA | Line boxes visually checked |
| 3 | D13-D20 | 13-20 Sep | Recognition and advisor integration | Tran Hoai Nam | Versioned CRNN inference, decoding, error review and guarded advisor provenance | Raw and advised text kept separate |
| 4 | D21-D26 | 21-26 Sep | Mobile, backend and verification | Both | Integrated capture-to-result workflow, feedback, consent and live metric rules | End-to-end sample reviewed |
| 5 | D27-D30 | 27-30 Sep | Evaluation and delivery | Both | Frozen evidence, regression QA, synchronized documents and final capstone package | Claim-safe handoff complete |

3.1  Review checkpoints

| Gate | Review | Exit condition |
| --- | --- | --- |
| D5 | Scope and evidence boundary | Confirm goals, excluded claims, metrics, architecture and responsibilities |
| D12 | Segmentation review | Inspect real notebook overlays and diacritic preservation |
| D20 | Inference and provenance | Check checkpoint identity, raw output, error notes and provider status labeling |
| D26 | Integrated workflow | Run one traceable mobile-to-backend-to-AI review path and verify inclusion rules |
| D30 | Final handoff | Validate all six deliverables as one consistent package |

3.2  Baseline timeline

| Day | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 |

4  Detailed Actions D1 to D15

Daily outputs and evidence for planning, data preparation and the start of recognition integration

| Day | Action | Owner | Deliverable | Evidence gate |
| --- | --- | --- | --- | --- |
| D1 | Define the user problem and Big Data course objective | Nguyen Van Duy Manh | Problem statement | User need and course alignment stated |
| D2 | Map stakeholders and the human review workflow | Nguyen Van Duy Manh | Workflow map | Decision authority remains with reviewer |
| D3 | Define research questions, scope and exclusions | Both | Scope baseline | Unsupported claims listed as out of scope |
| D4 | Audit dataset, checkpoint and evidence sources | Both | Evidence inventory | 59,462 / 500 and checkpoint identity recorded |
| D5 | Freeze architecture, metrics and acceptance criteria | Both | Planning gate record | Scope and evidence boundary approved |
| D6 | Review local handwriting sources and manifests | Both | Source review notes | Local candidates remain provisional |
| D7 | Validate manifests, consent and integrity fields | Nguyen Van Duy Manh | Data integrity checklist | No candidate is treated as verified by default |
| D8 | Establish the image preprocessing baseline | Tran Hoai Nam | Normalization pipeline | Illumination and ruling treatment documented |
| D9 | Implement crop and coordinate mapping | Tran Hoai Nam | Crop mapping | Image and review coordinates align |
| D10 | Integrate automatic line detection | Tran Hoai Nam | Detected line boxes | Boxes remain editable before OCR |
| D11 | Review overlays and Vietnamese diacritics | Nguyen Van Duy Manh | Visual QA evidence | Missed and merged lines recorded |
| D12 | Complete the segmentation checkpoint | Both | Segmentation gate record | Representative overlays inspected |
| D13 | Verify model, vocabulary and checkpoint identity | Tran Hoai Nam | Versioned inference manifest | Runtime matches the recorded handoff |
| D14 | Integrate packaged CRNN inference | Tran Hoai Nam | CRNN service path | Raw prediction stays traceable |
| D15 | Expose CTC decoding and raw line output | Tran Hoai Nam | Raw outputs | Confidence is not labeled as accuracy |

Daily evidence routine

| Capture | Check | Record | Escalate |
| --- | --- | --- | --- |
| Input, output and artifact identity | Acceptance criterion for the day | Decision, issue and evidence source | Any blocker that threatens the next gate |

5  Detailed Actions D16 to D30

Daily outputs and evidence for recognition review, integration, evaluation and delivery

| Day | Action | Owner | Deliverable | Evidence gate |
| --- | --- | --- | --- | --- |
| D16 | Analyse recognition errors and confidence limits | Both | Error review log | Keep raw scores, edits and uncertainty limits |
| D17 | Add guarded cloud advisor requests | Tran Hoai Nam | Advisor requests | Provider and model provenance visible |
| D18 | Preserve provider status and decision source | Tran Hoai Nam | Provider availability | No local candidate labeled cloud AI |
| D19 | Review advisor safety and provenance | Both | Advisor QA record | Raw OCR is never overwritten |
| D20 | Complete the inference and provenance checkpoint | Both | Integration gate record | Real provenance; unavailable output stays null |
| D21 | Connect mobile capture to backend and AI service | Both | Integrated request path | One image reaches detection and recognition |
| D22 | Persist page, crops and multiline trial | Tran Hoai Nam | Trial record | Stored IDs and image references resolve |
| D23 | Implement result polling and line review | Nguyen Van Duy Manh | Review interface | Pending advice merges without losing edits |
| D24 | Record feedback, consent and eligibility | Nguyen Van Duy Manh | Human verification flow | Eligibility does not trigger training |
| D25 | Implement paired reporting and separate history controls | Both | Reporting evidence | Same references; selected/all history deletion |
| D26 | Complete the end-to-end workflow checkpoint | Both | Integrated gate record | Traceable sample passes the full review flow |
| D27 | Freeze metrics and the evidence register | Both | Evidence freeze | All reported values have a declared source |
| D28 | Run regression, visual QA and claim review | Both | QA record | No fabricated or stale evidence remains |
| D29 | Synchronize all six submission artifacts | Both | Cross-document review | Names, dates, metrics and limits agree |
| D30 | Package six files and complete sign-off | Both | Final capstone package | Six files render and cross-check cleanly |

Finalization routine

| Evidence | Visual QA | Consistency | Handoff |
| --- | --- | --- | --- |
| Verify every reported count and metric | Render and inspect every page or slide | Cross-check names, dates and claim boundaries | Package only the six reviewed final files |

6  Roles, Risks and Quality Controls

Ownership is explicit while integration and final review remain shared

| Owner | Primary responsibilities | Accountability |
| --- | --- | --- |
| Nguyen Van Duy Manh | Scope and evidence review; line-review UX; feedback provenance; report and visual QA | Planning, verification and delivery evidence |
| Tran Hoai Nam | Preprocessing and line detection; CRNN integration; advisor orchestration; backend and AI runtime | Image-to-text implementation |
| Both | Architecture decisions; integration checkpoints; live analytics rules; regression and final handoff | End-to-end integrity |

6.1  Risk register

| Risk | Trigger | Mitigation | Owner |
| --- | --- | --- | --- |
| Unverified accuracy | Few usable external references | Exclude ineligible lines; show an explicit empty state; freeze an independent test manifest | Both |
| Diacritic or line loss | Detached marks, ruled paper or merged lines | Keep overlays editable and inspect representative failure cases | Tran Hoai Nam |
| Advisor over-correction | Suggestion changes a correct raw output | Preserve raw text, provenance and the reviewer’s selected result | Both |
| Privacy and consent | Notebook images may contain personal content | Require consent and integrity checks before dataset eligibility | Nguyen Van Duy Manh |
| Evidence drift | Screenshots or numbers no longer match code or data | Trace every claim to a source image, persisted provider output or checkpoint manifest; identify the evaluation denominator. | Both |
| Schedule compression | Late integration leaves insufficient QA time | Use D5, D12, D20, D26 and D30 as hard review gates | Both |

6.2  Reporting rules

Use CER 11.3388% only as the recorded checkpoint result on the declared 500-sample validation split.

Keep the 510 local candidates separate from the model split and label them pending review.

Report raw OCR, advisor-assisted text and final human text as distinct outputs.

Only tagged measured OCR scores are aggregated. They remain uncalibrated; provider-reported scores and human edits do not become OCR accuracy or AI gain.

6.3  Six-file delivery checklist

| File | Purpose | Final check |
| --- | --- | --- |
| Final report | Narrative, architecture, evidence and limitations | Render all pages; remove placeholders; verify figures |
| Defense deck | Twenty-slide defense narrative | Render all slides; check legibility, crops and metric consistency |
| Evaluation sheet | Official scoring form plus evidence reference | Keep evaluator score, comments, dates and signatures blank |
| WBS | Editable 30-day ownership and timeline | Validate dates, status list, print area and timeline fills |
| Action plan | Scope, method, daily actions, risks and approvals | Match project evidence and retain instructor review fields |
| Presentation script | Slide-by-slide speaking notes for all 20 slides | Match the final deck sequence, facts and limitations |

7  Instructor Review and Approval

The project team completes the plan; official assessment remains with the instructor

7.1  Planned review record

| Review area | Gate | Decision | Date |
| --- | --- | --- | --- |
| Scope and evidence boundary | D5 | □ Approved □ Revise |  |
| Data and line-detection evidence | D12 | □ Approved □ Revise |  |
| Recognition and advisor provenance | D20 | □ Approved □ Revise |  |
| Integrated review workflow | D26 | □ Approved □ Revise |  |
| Final six-file package | D30 | □ Approved □ Revise |  |

7.2  Instructor comments

7.3  Sign-off

| Team representative | Instructor / evaluator | Date |
| --- | --- | --- |
| Name and signature | Name and signature | DD / MM / YYYY |