## Cover Page
Big Data Course
HandAI Capstone Project
Work Breakdown Structure
30-Day Delivery Plan · 01–30 Sep 2026
Nguyen Van Duy Manh · Tran Hoai Nam
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
HandAI ¦ Big Data Course
CAPSTONE WORK BREAKDOWN STRUCTURE · 30-DAY DELIVERY BASELINE
PLAN PERIOD | 01/09/2026 – 30/09/2026 |  |  |  |  | REVIEW GATES D5 → D12 → D20 → D26 → D30
PROJECT TEAM | Nguyen Van Duy Manh · Tran Hoai Nam |  |  |  |  | Vietnamese Primary School Handwriting Recognition System
STATUS LEGEND | Done |  | In-progress |  | Delayed |  |  | Editable dates and statuses · timeline updates from the date range
TASK / WORKSTREAM | START | END | RESPONSIBILITY | DELIVERABLE | STATUS | W1 · D1–D7 | [6 empty] | W2 · D8–D14 | [6 empty] | W3 · D15–D21 | [6 empty] | W4 · D22–D28 | [6 empty] | W5
[6 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30
[6 empty] | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30
1. Planning & Evidence Audit | 2026-09-01 | 2026-09-05 | Both | Scope and evidence map | Done
1.1 Define user problem and course objective | 2026-09-01 | 2026-09-01 | Nguyen Van Duy Manh | Problem statement | Done
1.2 Map stakeholders and review workflow | 2026-09-02 | 2026-09-02 | Nguyen Van Duy Manh | Workflow map | Done
1.3 Define questions, scope and exclusions | 2026-09-03 | 2026-09-03 | Both | Scope baseline | Done
1.4 Audit datasets, model and claim boundaries | 2026-09-04 | 2026-09-04 | Both | Evidence inventory | Done
1.5 Freeze architecture, metrics and acceptance criteria | 2026-09-05 | 2026-09-05 | Both | D5 planning gate | Done
2. Data & Image Pipeline | 2026-09-06 | 2026-09-12 | Both | Reviewed image-to-line path | Done
2.1 Review sources, manifests and integrity | 2026-09-06 | 2026-09-07 | Both | Source and consent review | Done
2.2 Establish preprocessing baseline | 2026-09-08 | 2026-09-08 | Tran Hoai Nam | Image normalization | Done
2.3 Implement crop and coordinate mapping | 2026-09-09 | 2026-09-09 | Tran Hoai Nam | Aligned crop metadata | Done
2.4 Integrate automatic line detection | 2026-09-10 | 2026-09-10 | Tran Hoai Nam | Editable line regions | Done
2.5 Inspect overlays, diacritics and segmentation | 2026-09-11 | 2026-09-12 | Both | D12 segmentation gate | Done
3. Recognition & Advisor Integration | 2026-09-13 | 2026-09-20 | Tran Hoai Nam | Versioned inference path | Done
3.1 Verify model, vocabulary and checkpoint | 2026-09-13 | 2026-09-13 | Tran Hoai Nam | Inference manifest | Done
3.2 Integrate CRNN, CTC and raw output | 2026-09-14 | 2026-09-15 | Tran Hoai Nam | Raw line predictions | Done
3.3 Analyse errors and measured OCR-score limits | 2026-09-16 | 2026-09-16 | Both | Per-line scores and edit audit | Done
3.4 Add real advisor review and unavailable states | 2026-09-17 | 2026-09-18 | Tran Hoai Nam | Actual-provider provenance | Done
3.5 Review safety and inference provenance | 2026-09-19 | 2026-09-20 | Both | D20 integration gate | Done
4. Mobile, Backend & Verification | 2026-09-21 | 2026-09-26 | Both | Integrated review workflow | Done
4.1 Connect capture, backend and trial storage | 2026-09-21 | 2026-09-22 | Both | Persisted multiline trial | Done
4.2 Implement review, feedback and consent | 2026-09-23 | 2026-09-24 | Nguyen Van Duy Manh | Human verification flow | Done
4.3 Verify paired reports and separate history | 2026-09-25 | 2026-09-26 | Both | Counts, history CRUD and D26 gate | Done
5. Evaluation & Delivery | 2026-09-27 | 2026-09-30 | Both | Final capstone package | Done
5.1 Freeze metrics and evidence register | 2026-09-27 | 2026-09-27 | Both | Model handoff + actual GUI trial receipt | Done
5.2 Run regression, visual QA and claim review | 2026-09-28 | 2026-09-28 | Both | QA record | Done
5.3 Synchronize six submission artifacts | 2026-09-29 | 2026-09-29 | Both | Cross-document review | Done
5.4 Package six files and complete sign-off | 2026-09-30 | 2026-09-30 | Both | D30 final handoff | Done
Planning note: reconstructed 30-day baseline; dates do not prove daily execution. Audit refreshed 02 Oct 2026: 1 image / 1 GUI trial / 12 reference lines. Raw OCR 6/12 (50.00%); actual Groq 7/12 (58.33%), +8.33 pp. Raw CER 8/194 (4.12%), WER 9/48 (18.75%); AI CER 5/194 (2.58%), WER 5/48 (10.42%). Source: actual GUI trial; no new training or independent benchmark.